## Priority 1
Focus 1: Identifying for SMVF Status
| Goal: | Agencies serving SMVF to identify SMVF status using a common definition and practice
| Target Population: | Any agency serving SMVF (i.e., Healthcare, MH care, state agencies, BH, law enforcement, etc.)
Outcome Measures
1 | Increase number of agencies who have adopted utilization of the definition
2 | Increase the number of SMVF identified (representative of population?)
3 | Increase in referrals to SMVF resources
4
Strategy - (Brief Description or Pilot Name)
Inventory current practice for identifying SMVF among SMVF-serving organizations (e.g. who is asking for SMVF status, what questions are used to identify SMVF) Select agencies who should be using the common definition of SMVF (determine scope) Define how we ask the question about SMVF Status (“Have you Ever Served?”) *Implement the common definition and practices for identification of SMVF status across agencies serving SMVF through training, messaging and supporting adoption Develop comprehensive list of resources for SMVF referrals (in PA2 as well)
|  | Process Measures [How much/ How many?] | Action Item | By When | Resources Needed | Person(s) Responsible | Date of next review
| 1 | SMVF Status question(s) identified | Define how we ask the question |  | Lived Experience Perspective (to inform the process and for implementation)
| 2 | The completed inventory of who is asking Number of agencies selected to utilize the definition | Generate a list of agencies serving SMVF (hospitals, designated agencies, state agencies, law enforcement, schools, primary care, Division of Substance Use (DSU), preferred providers, housing and homless providers, economic services, child welfare, aging and independent living, helplines, SASH). |  | Input from agencies who are not currently using standard practice of identifying SMVF/suicide screening and inquire into process/protocols Tools and models (eg VISR, ATQ)
| 3 | Training pre/post surveys? Do you understand the goals utility, likelihood to use, suggestions for improvement? |  |  | Training for agencies on SMVF status and buy-in
| 4 | Policy developed | Establish criteria for selecting agencies to use the common definition |  | Implementation of policy
| 5 | Toolkit for implementation developed | Review ATQ/VISR/NH/Col Schwartz implementation toolkits and select Develop/implement VT toolkit |  | Incentive/resources to implement SVMF status ID
| 6 |  |  |  | Leadership Buy-In
| 7 | Number of agencies trained to utilize the definition |  |  | Implementation coordination; including time for staff training
8
Focus 2: Screening for Suicidal Ideation
| Goal: | Standardization and broadening the use of the Columbia Suicide Severity Rating Scale (C-SSRS)
| Target Population: | SMVF-specific serving organizations and programs (VFW, Legion, etc.) - Any organization or program with primary focus on SMVF
Outcome Measures
1 | Short:% and number of SMVF-serving organizations that adopt CSSRS
2 | Short:# of organizations reporting use of CSSRS to central repository
3 | Long:Increase identification of suicide risk among SMVF by serving organizations and programs
4 | Long:Increase in referrals to suicide-specific care among SMVF identified by CSSRS screening
5 | Long:Decrease in suicide death among SMVF
Strategy - (Brief Description or Pilot Name)
Identify SMVF organizations to adopt standard suicide risk screening Increase the # of SMVF organizations that adopt the CSSRS by providing resources, training and TA Improve statewide data on SMVF with suicidality (long term) Develop data and evaluation plan
|  | Process Measures [How much/ How many?] | Action Item | By When | Resources Needed | Person(s) Responsible | Date of next review
| 1 | Identification of SMVF organizations that should adopt CSSRS
| 2 | Development of training/TA plan |  |  | Incentive/resources to implement SVMF suicide screening Leadership Buy-In Implementation coordination, including time for staff training Resources (funding, etc) for training, implementation, and tracking
| 3 | Completion of CSSRS training/TA
| 4 | # of trainings, # trained, % of organizations participating
| 5 | Awareness of the training # and type of trainings offered
6
7
| Goal: | Increase MHFA/Suicide Awareness and Support training for service members
| Target Population: | SMVF
Outcome Measures
1 | Short: % and # trainees that feel comfortable talking about suicide and know how to support someone who identifies as suicidal (post survey)
2 | Long: Decrease in suicide death among SMVF
Strategy - (Brief Description)
Increase MHFA/Suicide Awareness and Support training for service members Develop plan for MHFA/ Suicide Awareness and Support training
|  | Process Measures [How much/ How many?] | Action Item | By When | Resources Needed | Person(s) Responsible | Date of next review
| 1 | Development of training/TA plan | Consult with Miriam and Andre about which SMVF specific organizations we should approach/include |  | Incentive/resources to implement MHFA/Suicide Awareness and Support training Resources (funding, etc) for training, implementation, and tracking
|  |  | Initiate stakeholder engagement with SMVF specific organizations and assess current practices around MHFA/Suicide Awareness and Support and how to engage SMVF individuals |  | Leadership Buy-In
| 2 | % trained entities/individuals trained in MHFA/ Suicide Awareness and Support training |  |  | Resources for tracking
3
4
5
6
7
8
Goal:
Target Population:
Outcome Measures
1
2
Strategy - (Brief Description)
Strategy detail
|  | Process Measures [How much/ How many?] | Action Item | By When | Resources Needed | Person(s) Responsible | Date of next review
1
2
3
4
5
6
7
8
Note on A1: Select from dropdown menu
Note on A23: Select from dropdown menu
Note on B3: What is the coalition trying to achieve? (Plug in strategies from strategy selection process.)
Note on B5: What is the coalition trying to achieve? (Plug in strategies from strategy selection process.)
Note on B25: What is the coalition trying to achieve? (Plug in strategies from strategy selection process.)
Note on B27: What is the coalition trying to achieve? (Plug in strategies from strategy selection process.)
Note on B52: What is the coalition trying to achieve? (Plug in strategies from strategy selection process.)
Note on B54: What is the coalition trying to achieve? (Plug in strategies from strategy selection process.)
Note on B72: What is the coalition trying to achieve? (Plug in strategies from strategy selection process.)
Note on B74: What is the coalition trying to achieve? (Plug in strategies from strategy selection process.)
Note on C11: Add brief description if applicable. Include target audience.
Note on C13: What needs to happen to get this strategy in motion?
Note on C34: Add brief description if applicable. Include target audience.
Note on C36: What needs to happen to get this strategy in motion?
Note on C58: Add brief description if applicable. Include target audience.
Note on C60: What needs to happen to get this strategy in motion?
Note on C78: Add brief description if applicable. Include target audience.
Note on C80: What needs to happen to get this strategy in motion?
Note on F13: What does the coalition need to carry out this action item?
Note on F36: What does the coalition need to carry out this action item?
Note on F60: What does the coalition need to carry out this action item?
Note on F80: What does the coalition need to carry out this action item?

## Priority 2
Focus 1: Promoting Connectedness
| Goal: | Increase awareness of existing resources for SMVF to facilitate access to care across systems at all levels of the continuum.
| Target Population: | SMVF-serving organizations and programs, Community, Health Care Providers, Educators, Community Mental Health and Social Service agencies, Faith based organizations SMVF Peer community
Outcome Measures
1 | Short: Map of current state of SMVF resources
2 | Short: Baseline data on current knowledge of referral sources
3 | Short: Continue to conduct provider surveys on current knowledge base of SMVF-specific issues and suicide prevention strategies to track progress of efforts
4 | Long: Identification of and problem solving for gaps in resources
5 | Long: Follow up data to look at success of educational awareness strategies:
6 | Long: Community orgs know how to support SMVF, know where to refer those in need
Strategy - (Brief Description)
1-Create a map of existing and available SMVF resources 2- Create an awareness/education campaign of available resources for SMVF in Vermont 3- Increasing resources to share points of information and how to access support access for to SVMF. Expand providers & community and provider network knowledge of how to best provide support
|  | Process Measures [How much/ How many?] | Action Item | By When | Resources Needed | Person(s) Responsible | Date of next review
| 1 |  | Identify software tool (Map Box)
| 2 |  | Identify SME: human services, education, mental health, faith based |  | Invite other relevant players to the table to inform and review efforts
| 3 | Provider surveys on current knowledge base of SMVF-specific issues, in order to assess and address knowledge gaps Map of current state of SMVF resources | create standard form to gather comprehensive information across all branches of services and civilians
| 4 |  | Potential work with VDH in campaign/awareness |  | Connect with VDH grant team for communication and campaign support
| 5 | Development of an awareness campaign |  |  | Develop outreach materials for providers and community members which could include magnets, QR codes ,handouts Education/ Awareness- communication to promote coordination and referral
| 6 | Pre/post community survey of SMVF-serving organizations and programs -Pre Awareness for Resources Post Awareness, Accessibility, satisfaction, improvement
7
8
Focus 2: Care Transitions
| Goal: | Increase awareness of existing resources for SMVF to facilitate access to care across systems at all levels of the continuum.
1 | Target Population:
2 | Outcome Measures
Short: Perceptions of SMVF: -were they linked to additional care in a timely manner -did they receive all needed services
Short: increase in utilization of support resources
Long: Reductions in first time and repeat emergency room visits
Long: Reduction in suicide attempts among those screening high risk
Strategy - (Brief Description)
1-Create a map of existing and available SMVF resources 2- Create an awareness/education campaign of available resources for SMVF in Vermont 3- Increasing resources to share points of information and how to access support access for to SVMF. Expand providers & community and provider network knowledge of how to best provide support
|  | Process Measures [How much/ How many?] | Action Item | By When | Resources Needed | Person(s) Responsible | Date of next review
| 1 | Assessment of current SMVF suicide risk follow up practices |  |  | Assess existing follow up policies pending a positive suicide screening or suicide attempt, and determine whether it is necessary for the state to identify or streamline best practices Assess viability of peer-based follow-ups using existing SMVF peer support resources
| 2 | A written summary of best practices for follow up to SMVF identified as at high risk of suicide
| 3 | Create recommendations for improvements based off of gap analysis |  |  | To integrate SMVF efforts with other suicide prevention efforts related to follow up care
| 4 | Provide evidence of stakeholder engagement to inform involvement |  |  | Engage in stakeholder involvement
| 5 |  |  |  | Better understanding of insurance barriers to care for SMVF
6
7
Note on A1: Select from dropdown menu
Note on A27: Select from dropdown menu
Note on B3: What is the coalition trying to achieve? (Plug in strategies from strategy selection process.)
Note on B5: What is the coalition trying to achieve? (Plug in strategies from strategy selection process.)
Note on B30: What is the coalition trying to achieve? (Plug in strategies from strategy selection process.)
Note on B32: What is the coalition trying to achieve? (Plug in strategies from strategy selection process.)
Note on C13: Add brief description if applicable. Include target audience.
Note on C15: What needs to happen to get this strategy in motion?
Note on C38: Add brief description if applicable. Include target audience.
Note on C40: What needs to happen to get this strategy in motion?
Note on F15: What does the coalition need to carry out this action item?
Note on F40: What does the coalition need to carry out this action item?

## Priority 3
Focus 1: Safety Planning (Some of this seems like Priority 1 with ATQ: You may want to coordinate with priority group 1).
| Goal: | Broaden and standardize the use of empirically supported safety plans across Eds
| Target Population: | Providers and points of contact in EDs who work with SMVF
Outcome Measures
1 | Short: Increased knowledge and skills related to safety planning.
2 | Short: Increase in the number of SMVF with suicide risk who have documented Stanley Brown plans.
3 | Short: Adopting CALM (with hopes and dreams of enhancing Stanley Brown in the second phase)
4 | Long: Reduction in suicide attempts and deaths among SMVF.
Strategy - (Brief Description)
Increase the use and consistency of use of the Stanley Brown safety plans in EDs, including having them in electronic health records.
|  | Process Measures [How much/ How many?] | Action Item | By When | Resources Needed | Person(s) Responsible | Date of next review
| 1 | Number of EDs participating in the needs assessment. (all ED have done a needs assessment for the VAST project) | Review results from needs assessment (VDH VAST).
| 2 | Number of EDs and individuals participating in trainings and subsequently adopting the Stanley Brown. % of EHRs using the Stanley Brown consistently in the presence of identified suicide risk. Documentation of the use of the Stanley Brown in EHRs. | ID EDs that are not using the SB or equallivant |  | awareness of urgent care practices around risk assessment and safety planning
| 3 |  | look for champion in each ED department- to get buy-in for ED's, and to arrange for training or grand rounds |  | Staff support for spreading safety planning. Funding / incentives for adoption of safety planning (what is the carrot?)
| 4 |  | develop training package & grand rounds workshop, get CME approval |  | Training for providers specific to safety planning.
| 5 |  | medical school idea: work to get lethal means training into initial training. (Tom or Dr. Lopez)
| 6 |  | Dr Dickerson (via Klein): Make a standardized patient for interaction for education.
| 7 |  |  |  | Federal change to CDC-ESSENCE to include “ask the question” about SMVF status. Better ID of SMVF individuals and documentation of safety plans in EDs.
8
9
Focus 2: Lethal Means Safety
| Goal: | Promote safe storage of medications and poisons.
Target Population:
Outcome Measures
1 | Short: Providers have increased knowledge and skills related to medication risk assessment and counseling.
2 | Short: Intentions to promote/distribute safe storage options to patients/customers?
4 | Long: Increased safe storage practices among SMVF.
5 | Long: Reduction in medication-related suicide attempts and mortality.
Strategy - (Brief Description)
Assess needs and then distribute medication safe storage devices to reduce access to lethal means during times of crisis. Three component pieces of work: 1) needs assessment (ED vs PCP), 2) develop guidance / materials to accompany devices, 3) distribute devices. Research initial and sustain funding for acquiring and distributing medication lock boxes
|  | Process Measures [How much/ How many?] | Action Item | By When | Resources Needed | Person(s) Responsible | Date of next review
Need to do an initial needs assessment of medication safe storage screening, counseling & device distribution; can be complemented by CSP Stakeholder survey.
Supply of lock boxes (based on setting) and to ID funding sources (ask Paul, others)
| 1 | Number of organizations completing needs assessment. | develop and launch and analyze needs assessment |  | May need to alter safety plan to better capture medication lock box needs and distribution. Change (update) the relevant BRFSS questions.
| 2 |  | develop a distribution plan
| 3 | Number of devices distributed – to organizations, and from organizations to individuals. Number of organizations distributing devices. | ID organizations interested in giving out LMSS devices |  | Link with AAAs. (What is AAAs?)
| 4 |  | outreach to them (them being organizations?)
| 5 |  | identify "lead" org
| 6 |  | develop reporting system
| 7 |  | are we limited to Vets or "everyone"
| 8 | Coverage/access across the state | plan to pilot and scale the program |  | Need to take into account message differences for teens/YAs/family members versus veterans.
(ED. vet outreach peeps, DA's?)
do we want to limit to just giving organizations OR individuals? (cost/ benefit?)
developing resources map to raise awareness
# ED that hit a min. % providers trained. (goal to have 50% of providers trained with Stanely Brown)
Participation in outreach and education.
Note on A1: Select from dropdown menu
Note on A25: Select from dropdown menu
Note on B3: What is the coalition trying to achieve? (Plug in strategies from strategy selection process.)
Note on B5: What is the coalition trying to achieve? (Plug in strategies from strategy selection process.)
Note on B27: What is the coalition trying to achieve? (Plug in strategies from strategy selection process.)
Note on B29: What is the coalition trying to achieve? (Plug in strategies from strategy selection process.)
Note on C11: Add brief description if applicable. Include target audience.
Note on C13: What needs to happen to get this strategy in motion?
Note on C35: Add brief description if applicable. Include target audience.
Note on C37: What needs to happen to get this strategy in motion?
Note on F13: What does the coalition need to carry out this action item?
Note on F37: What does the coalition need to carry out this action item?

## Sample
Priority Area: 3 | Increase Lethal Means Safety and Safety Planning
Focus | Strategy/Goal | Program/Policy Name (can fill in later) | Brief Description | Action Item | How much/ How many? | By When | Outcome Measures | Resources Needed | Person(s) Responsible | Date of Next Review
Increase Lethal Means Safety | Increase use of safe firearm storage options in the Veteran community | Program A (name TBD - possibly "Secure It Howard County" Gun Shop Outreach) | Multi-pronged outreach and training effort to increase awareness and options for safe firearm storage in Veteran community | Gather educational materials | 500 flyers | 2021-12-01 | (Process measure: # of flyers printed) | Flyers | Jenna S. | 2021-11-01
|  |  |  | Conduct outreach to local gun shops | 5 gun shops | 2022-02-01 | Change in gun shop owners' awareness around importance of safe firearms storage | Educational materials for gun shop owners Volunteers to do outreach | Jenna S. | 2021-12-01
|  |  |  | Schedule trainings | 5 trainings scheduled | 2022-03-01 | (Process measure: # of trainings scheduled) | none | Jenna S. | 2022-02-01
|  |  |  | Provide trainings | 5 trainings completed | 2022-05-01 | Change in attendees' knowledge and self-efficacy of safe firearms storage practices pre- and post-training | Trainers to conduct trainings; evaluation survey | Jenna S. | 2022-04-01
|  |  |  | Monitor progress and outcomes | n/a | Ongoing | Change in # of firearms stored at gun shops before and after pilot | Tracking system for # of firearms stored | Alex T. | 2022-02-01
|  | Program B (name TBD - possibly "Secure It Howard County" VSO Outreach) | Strategy 2 | Distribute educational materials to Veterans through VSOs | 10 VSOs | 2022-01-15 | Change in Veterans' knowledge around importance of safe firearm storage before and after distribution | Educational materials for Veterans Connections with VSOs | Tim A. | 2021-10-01
|  | CALM Training - Community Providers | n/a | Conduct CALM training with community providers | 50 community providers | 2022-02-01 | Change in community providers' self-efficacy to talk to Veterans about safe storage | Connections with community providers | Aaron E. | 2021-10-01
|  | Program C (name TBD) | n/a | Develop online database of storage options in the community | 1 database | 2022-04-01 | # of hits to website that lists the database | List of storage options Web developer | Jenna S. | 2021-11-01